# Business Proposal: AI Agentic UA Engine

Table of Contents

# Business Proposal: AI Agentic UA Engine

Prepared by: Solutions Architect (AI-assisted) Date: 2026-03-13 Audience: Leadership / Stakeholders Export: Run /plan-export to generate .docx version

## Executive Summary

We propose building an AI-powered User Acquisition Engine that automates the full advertising cycle — from campaign planning to creative production, deployment, and real-time optimization — across Facebook, Google, and TikTok.

The system replaces manual, repetitive UA workflows with AI agents that make data-driven decisions 24/7, while keeping humans in control of high-risk budget decisions.

Bottom line: This engine can reduce creative production costs by 50-70%, compress campaign launch time from weeks to minutes, and improve ROAS by 15-25% — starting with a 10-week, $5K pilot on TikTok.

## The Problem

| Challenge | Current State | Business Impact |
| --- | --- | --- |
| Slow campaign launches | 2-4 weeks to go from idea to live ad | Missed market windows, slow reaction to trends |
| Expensive creative production | Manual design for each variant | High cost, low testing volume (5-10/week) |
| Reactive optimization | Managers check dashboards daily | 4-24 hour reaction to anomalies, wasted spend |
| Rising UA costs | CPI increasing 20-30% YoY | Margins shrinking without ROAS improvement |
| Talent bottleneck | Need 3-5 UA people per game | Hard to scale to more titles |

## The Solution

An AI engine built on 3 layers:

┌──────────────────────────────────────────────────────────┐
│                   AI Agentic UA Engine                    │
│                                                          │
│  ┌──────────────┐  ┌─────────────┐  ┌────────────────┐  │
│  │ n8n          │  │ Dify        │  │ OpenClaw       │  │
│  │ Orchestrator │──│ AI Brain    │──│ API Gateway    │  │
│  │ (Workflows)  │  │ (Agents)    │  │ (Connections)  │  │
│  └──────────────┘  └─────────────┘  └────────────────┘  │
│                                                          │
│  ┌────────────────────────────────────────────────────┐  │
│  │          Existing AppsFlyer Data Pipeline           │  │
│  │    (Real-time attribution, user data, revenue)      │  │
│  └────────────────────────────────────────────────────┘  │
└──────────────────────────────────────────────────────────┘

### What the AI Does

| Pillar | Before (Manual) | After (AI Engine) |
| --- | --- | --- |
| Planning | UA manager analyzes spreadsheets, sets budgets | AI agent analyzes AppsFlyer data, generates optimized campaign plans |
| Creative | Designers create 5-10 variants manually | AI generates 50-100 variants using GenAI tools (Creatify, OpenArt.ai) |
| Deployment | Manual upload to each ad platform | Automated deployment to TikTok, Facebook, Google in minutes |
| Monitoring | Check dashboards 1-2x daily | AI monitors 24/7, auto-pauses bad ads, alerts on anomalies |
| Optimization | Weekly manual adjustments | Continuous AI-driven optimization with human approval for big changes |

### Safety: Human-in-the-Loop

The AI doesn’t operate unchecked. Three tiers of control:

| Tier | AI Authority | Example |
| --- | --- | --- |
| 🟢 Full Auto | AI acts immediately | Pause underperforming ads, scale budget ≤20% |
| 🟡 Semi-Auto | AI recommends, human approves via Slack | New campaigns, budget changes >20% |
| 🔴 Human Only | Human decides entirely | Total budget allocation, brand direction |

## Expected Impact

| Metric | Current | With AI Engine | Improvement |
| --- | --- | --- | --- |
| Campaign launch time | 2-4 weeks | < 2 days (15 min automated) | 95%+ faster |
| Creative variants per week | 5-10 | 50-100 | 10x more testing |
| Production costs | Baseline | -50% to -70% | Significant savings |
| ROAS | Baseline | +15% to +25% | Higher returns |
| Anomaly reaction time | 4-24 hours | < 1 hour | 20x faster |
| UA headcount per game | 3-5 people | 1-2 people | 60% reduction |

## Investment & Timeline

### 10-Week Pilot Plan

gantt
    title AI UA Engine — Pilot Timeline
    dateFormat YYYY-MM-DD
    axisFormat %b %d

    section Build
    Foundation + Planning Agent    :a1, 2026-03-17, 14d
    Creative Pipeline + Deploy     :a2, after a1, 14d
    Monitoring + HITL              :a3, after a2, 14d
    
    section Gate
    REVIEW GATE                    :crit, milestone, gate, after a3, 0d

    section Scale
    Multi-Platform Expansion       :a4, after gate, 14d
    Analytics + Handoff            :a5, after a4, 14d
    LAUNCH                         :crit, milestone, launch, after a5, 0d

### Cost Breakdown

| Category | Pilot (10 weeks) | Monthly (Production) | Annual (Scaled) |
| --- | --- | --- | --- |
| Engineering | Internal (1-2 FTE) | Internal | Internal |
| Ad spend (TikTok pilot) | $5,000 | $8-20K/mo | $100-600K/yr |
| LLM API costs | ~$50 | ~$50-150/mo | ~$600-1,800/yr |
| GenAI tool subscriptions | Free tiers | ~$60/mo | ~$720/yr |
| Infrastructure | $0 (local dev) | ~$100/mo | ~$1,200/yr |
| Total (excl. ad spend) | ~$50 | ~$310/mo | ~$4,320/yr |

Key insight: The engine costs ~$4,300/year to operate (excluding ad spend). Even a 1% ROAS improvement on $100K annual ad spend would save $1,000+ — the system pays for itself with minimal improvement.

### ROI Projection

| Scenario | Annual Ad Spend | ROAS Improvement | Additional Revenue | ROI |
| --- | --- | --- | --- | --- |
| Conservative | $100K | +10% | +$10K | 2.3x |
| Target | $300K | +20% | +$60K | 14x |
| Optimistic | $600K | +25% | +$150K | 35x |

Plus: headcount savings of 2-3 FTE per game × salary

## Risk Management

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| AI makes bad budget decisions | Low | 6 anti-hallucination guardrails enforce hard limits |
| AI-generated creatives underperform | Medium | Quality gate + A/B test before scaling |
| Ad platform blocks automation | Low | Official APIs only, comply with ToS |
| System downtime disrupts campaigns | Low | Manual fallback always available |
| Pilot doesn’t show lift | Medium | Review Gate at Week 6 — pivot before further investment |

## Why Now?

- AI-generated creatives are mainstream — 30-40% of top publishers already use GenAI

- UA costs rising 20-30% YoY — automation is the only way to maintain margins

- We already have the data infrastructure — AppsFlyer pipeline gives us real-time signals

- Team has the skills — n8n and Dify experience means fast time-to-value

- Low-risk pilot — $5K investment validates the approach before committing

## Decision Requested

Approve the 10-week pilot to validate the AI UA Engine on 1 game (Total Football) with TikTok Ads.

| What We Need | From Whom |
| --- | --- |
| Engineering allocation (1-2 FTE, 10 weeks) | Engineering Lead |
| TikTok Ads pilot budget ($500/week × 10 weeks) | Marketing / Finance |
| API keys for TikTok, GenAI tools | UA Team |
| Weekly 1-hour review sessions | UA Manager |
| Production server access (Week 5+) | DevOps / IT |

Success criteria at Week 6 Review Gate: - AI-managed campaigns achieve comparable or better CPI vs. manual - Creative production is ≥5x faster - System operates reliably with <1hr anomaly response

If the gate passes → expand to Facebook and Google (Sprints 4-5). If it doesn’t → lessons learned documented, minimal investment lost.

## Appendix: Key Documents

| Document | Contents |
| --- | --- |
| Overview | Requirements, NFRs, integrations, HITL framework |
| Research | Build-vs-buy analysis, API feasibility, PoCs |
| Tech Stack | Technology evaluations with ADR-format decisions |
| Architecture | C4 diagrams, data contracts, security, deployment |
| Implementation Plan | Sprint tasks, Gantt chart, milestones |
| Technical Handoff | Developer-ready setup guide |
| Findings | All 15 ADRs, risk log, session notes |

💡 Tip: Run /plan-export to export this proposal as a formatted .docx for presentation.